## Sheet1
Date : 04 Apr 2016
S.No. | Module | Feature | Current Status / Specifications / (%) of work done | Estimated Start date | Estimated End date | % Completion | Status | Actual Start date | Actual End date
1 | Automation Reporting | Siebel Execution Results |  | 2016-03-03 | 2016-03-03 | 100% | Completed | 2016-03-11 | 2016-03-11
|  | Oracle |  | 2016-03-03 | 2016-03-03 | 100% | Completed | 2016-03-11 | 2016-03-14
|  | Tallyman |  | 2016-03-04 | 2016-03-04 | 100% | Completed | 2016-03-11 | 2016-03-14
|  | Safe ST |  | 2016-02-24 | 2016-02-25 | 100% | Completed | 2016-02-28 | 2016-03-14
|  | Siebel test data report |  | 2016-03-08 | 2016-03-08 | 100% | Completed | 2016-02-26 | 2016-02-29
2 | Test Assisting Tools | Siebel Test Data Request Tracker |  | NA | NA | 100% | Completed | NA | NA
|  | Siebel Test Data Request Form | Pending - File Upoad, Email send. | 2016-03-01 | 2016-03-01 | 70% |  | 2016-02-26
3 | Test Environment Details | NPE Environment Details |  | NA | NA | 100% | Completed | NA | NA
|  | PT Environment Availability |  | NA | NA | 100% | Completed | NA | NA
4 | Home | Login Form |  | 2016-03-07 | 2016-03-07 | 100% | Completed |  | 2016-03-22
|  | Session Module | Injection of session controller to all the controllers
5 | Admin | Test Data Request Tracker Admin |  | 2016-02-25 | 2016-02-26 | 100% | Completed
|  | Admin Dashboard |  | 2016-03-09 | 2016-03-09 | 100% | Completed
|  | System Details |  | 2016-03-09 | 2016-03-09 | 100% | Completed | 2016-03-07 | 2016-03-08
|  | Automation Matrices | Pending - Bar charts. | 2016-03-11 | 2016-03-11 | 50%
|  | Automation DSR |  | 2016-03-12 | 2016-03-12 | 100% |  |  | 2016-03-29
6 | Automation Suite | Siebel Tosca Suites |  | 2016-03-15 | 2016-03-15 | 100% | Completed | 2016-03-09 | 2016-03-11
|  | Siebel Test data Suites |  | 2016-03-16 | 2016-03-16 | 100% | Completed | 2016-03-09 | 2016-03-11
|  | Oracle - Tosca Suites |  | 2016-03-17 | 2016-03-17 | 100% | Completed | 2016-03-09 | 2016-03-11
|  | Fusion ST - safe suite |  | 2016-03-18 | 2016-03-18 | 100% | Completed |  | 2016-03-24
|  |  |  | 2016-03-19 | 2016-03-19 | 100% |  |  | 2016-03-31
|  | Fusion ST - safe modify |  |  |  | 100% | Completed |  | 2016-03-29